## Dashboard
Project Dashboard
Project Name | Planned estimates
Integra CKYC Gateway | Schedule | 25 | Weeks |  |  | PV, EV, AC Graph
| Effort | 212 | Person days
Project start date | 2022-09-30 | Project end date |  | 2023-03-01
Status of the project on | 2023-01-23 | What does it mean?
Are we ahead or behind schedule? | -83.02% | The project is running behind schedule
How efficiently are we using our time? | 16.98% | Project is running at 17 percent efficiency
When is the project likely to complete? | 147.2222 | As on date, project will take 147 weeks to complete
Are we under or over budget? | -450% | The project is 450 percent over budget
How efficiently are we using our resources? | 18.18% | For each dollar spent, 18 cents are recovered
What is the remaining work likely to cost? | 957 | As on date, project will take 957 person days to complete
What is the entire project likely to cost? | 1155 | #N/A
How much will we be under or over budget? (Assuming the current trend to continue) | -355.7% | On completion, the project will be 356 percent over budget if current trend continues
How much will we be under or over budget? (Assuming the current trend will not continue) | -77.14% | On completion, the project will be 77 percent over budget if corrective actions are taken to remove the causes of variance as on date
How much of the total effort have been used till date? | 94.29% | As on date, 94 percent of effort have been used yielding 17 percentage of work product.
Health check summary report |  |  | Top five issues in the project |  | Top five risks
Date of report | 2023-01-23 |  | 1 | 0 | 1 | 0
Project Name | Integra CKYC Gateway |  | 2 | 0 | 2 | 0
Project ID | IMSICGD1 |  | 3 | 0 | 3 | 0
Project Manager | Harikrishna E |  | 4 | 0 | 4 | 0
PQA | 0 |  | 5 | 0 | 5 | 0
Number of team members | 9
Process Compliance | 89.39%
Process non-compliance | 10.61%
SCM Compliance | 93.1%
SCM Non-compliance | 6.897%

## Team
| Project Name | Integra CKYC Gateway | Project ID | IMSICGD1
| Starte date | 2022-09-30 | End date | 2023-03-01
| Planned schedule (weekS) | 25 | Estimated effort (pd) | 212
| Customer Name | INTEGRA | CPC | Internal
| PM | Harikrishna E | SA | Shailesh Ajmera
| PL | Satyanarayana | PQA
Sl No | Project Team | Role | Date of joining the project | Date of leaving the project
1 | Pulok Barik | Developer | 2022-09-30
2 | Vaishnavi | Developer | 2022-09-30
3 | Nafeesa NS | Developer | 2022-09-30
4 | Suma Devi | Developer | 2022-09-30
5 | Monika | Tester | 2022-09-30
6 | Lavanya | Test Lead | 2022-09-30
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Deliverables
List of deliverables of the project |  | Select the current phase |  | Testing
Sl No. | Name of the artefact | Internal Deliverable | Customer Deliverable | Phase | Completed | Review | Review Record | Review Checklist | SVN | Total
1 | Document of Understanding | N | N | Pre sales | [5 empty] | 0
2 | Architecture Document | N | N | Pre sales | [5 empty] | 0
3 | Proposal | N | N | Pre sales | [5 empty] | 0
4 | Contract | N | N | Pre sales | [5 empty] | 0
5 | Estimation | Y | N | Requirement | 1 | 1 | 1 | 0 | 1 | 4
6 | PMP | Y | N | Requirement | 1 | 1 | 1 | 0 | 1 | 4
7 | QAP | Y | N | Requirement | 1 | 1 | 1 |  | 1 | 4
8 | CMP | Y | N | Requirement | 1 | 1 | 1 |  | 1 | 4
9 | RMP | Y | N | Requirement | 1 | 1 | 1 |  | 1 | 4
10 | SRS | Y | N | Requirement | 1 | 1 | 1 | 1 | 1 | 5
11 | Requirement Traceability Matrix | Y | N | Requirement | 0 | 0 | 0 | 0 | 0 | 0
12 | Prototype/POC | N | N | Analysis | [5 empty] | 0
13 | Re-estimation-1 | N | N | Analysis | [5 empty] | 0
14 | Acceptance Test Plan | N | N | Analysis | [5 empty] | 0
15 | Acceptance Test Specification | N | N | Analysis | [5 empty] | 0
16 | HLD | Y | N | Design | 1 | 1 | 1 |  | 1 | 4
17 | System Test Plan | Y | N | Design | 1 | 1 | 1 |  | 1 | 4
18 | System Test Specification | Y | N | Design | 1 | 1 | 1 |  | 1 | 4
19 | LLD | N | N | Design | [5 empty] | 0
20 | Integration Test Plan | N | N | Design | [5 empty] | 0
21 | Integration Test Specification | N | N | Design | [5 empty] | 0
22 | Re-estimation-2 | N | N | Design | [5 empty] | 0
23 | Unit Test Plan | N | N | Development | [5 empty] | 0
24 | Unit Test Specification | Y | N | Development | 1 | 1 | 1 |  | 1 | 4
25 | Source Code | Y | N | Development | 1 | 1 | 1 |  | 1 | 4
26 | Unit Test Report | Y | N | Development | 1 | 1 | 1 |  | 1 | 4
27 | Integration Test Report | N | N | Testing | [5 empty] | 0
28 | System Test Report | Y | Y | Testing | 1 | 1 |  |  | 1 | 3
29 | User Manual | Y | Y | Testing | 1 | 1 |  |  | 1 | 3
30 | Online Help | N | N | Testing | [5 empty] | 0
31 | Installation Guide | N | N | Testing | [5 empty] | 0
32 | Release readiness check | Y | Y | Delivery | [5 empty] | 0
33 | Delivery note | Y | Y | Delivery | 1 |  |  |  | 1 | 2
34 | Release note | Y | Y | Delivery | 1 |  |  |  | 1 | 2
|  |  | 1 | Requirement
|  |  | 2 | Analysis (SRS)
|  |  | 3 | Design
|  |  | 4 | Development
|  |  | 5 | Testing
|  |  | 6 | Delivery
Note on C2: ====== ID#AAAAoxV_4E8 Bhaskar Jyoti Phukan (2023-01-20 14:37:16) Please do not remove any item from the list.

## Schedule
Over all schedule of the project. All data relating to schedule should be entered in this page only!
Sl No | Phase | Major work product | Del | Planned |  | No of days | Revised1 |  | No of days | Revised2 |  | No of days | Actual |  | No of days
|  |  |  | Start date | End date |  | Start date | End date |  | Start date | End date |  | Start date | End date
1 | Pre sales | Document of Understanding | N | [11 empty] | 0
2 | Pre sales | Architecture Document | N | [11 empty] | 0
3 | Pre sales | Proposal | N | [11 empty] | 0
4 | Pre sales | Contract | N | [11 empty] | 0
5 | Requirement | Estimation | Y | 2022-10-03 | 2022-10-03 | [7 empty] | 2022-10-03 | 2022-10-03 | 0
6 | Requirement | PMP | Y | 2022-10-04 | 2022-10-10 | [7 empty] | 2022-10-04 | 2022-10-10 | 0
7 | Requirement | QAP | Y | 2022-10-04 | 2022-10-04 | [7 empty] | 2022-10-05 | 2022-10-06 | 0
8 | Requirement | CMP | Y | 2022-10-05 | 2022-10-06 | [7 empty] | 2022-10-05 | 2022-10-06 | 0
9 | Requirement | RMP | Y | 2022-10-06 | 2022-10-07 | [7 empty] | 2022-10-06 | 2022-10-07 | 0
10 | Requirement | SRS | Y | 2022-10-06 | 2022-10-12 | [7 empty] | 2022-10-07 | 2022-10-14 | 0
11 | Requirement | Requirement Traceability Matrix | Y | 2022-10-13 | 2022-10-13 | [7 empty] | 2022-10-14 | 2022-10-14 | 0
12 | Analysis | Prototype/POC | N | [11 empty] | 0
13 | Analysis | Re-estimation-1 | N | [11 empty] | 0
14 | Analysis | Acceptance Test Plan | N | [11 empty] | 0
15 | Analysis | Acceptance Test Specification | N | [11 empty] | 0
16 | Design | HLD | Y | 2022-10-13 | 2022-10-25 | [7 empty] | 2022-10-17 | 2022-10-31 | 0
17 | Design | System Test Plan | Y | 2022-10-13 | 2022-10-21 | [7 empty] | 2022-10-14 | 2022-10-26 | 0
18 | Design | System Test Specification | Y | 2022-10-24 | 2022-11-24 | [7 empty] | 2022-10-27 | 2022-11-28 | 0
19 | Design | LLD | N | [11 empty] | 0
20 | Design | Integration Test Plan | N | [11 empty] | 0
21 | Design | Integration Test Specification | N | [11 empty] | 0
22 | Design | Re-estimation-2 | N | [11 empty] | 0
23 | Development | Unit Test Plan | N | [11 empty] | 0
24 | Development | Unit Test Specification | Y | 2022-10-25 | 2022-11-04 | [7 empty] | 2022-11-02 | 2022-11-11 | 0
25 | Development | Source Code | Y | 2022-11-02 | 2022-12-14 | [7 empty] | 2022-11-07 | 2022-12-19 | 0
26 | Development | Unit Test Report | Y | 2022-12-05 | 2023-01-02 | [7 empty] | 2022-12-07 | 2023-01-09 | 0
27 | Testing | Integration Test Report | N | [11 empty] | 0
28 | Testing | System Test Report | Y | 2023-01-03 | 2023-02-07 | [7 empty] | 2023-01-10 | 2023-02-16 | 0
29 | Testing | User Manual | Y | 2023-02-06 | 2023-02-20 | [7 empty] | 2023-02-10 |  | 0
30 | Testing | Online Help | N | [11 empty] | 0
31 | Testing | Installation Guide | N | [11 empty] | 0
32 | Delivery | Release readiness check | Y | 2023-02-21 | 2023-02-27 | [9 empty] | 0
33 | Delivery | Delivery note | Y | 2023-02-28 | 2023-03-01 | [9 empty] | 0
34 | Delivery | Release note | Y | 2023-02-27 | 2023-03-01 | [9 empty] | 0

## Effort
Effort distribution in the project
Planned effort for the project (pd) |  |  | 212 |  | Distributed so far |  | 211
Sl No | Phase | Major work product | Del | Planned Effort (pd) | Revised-1 Effort (pd) | Revised-2 Effort (pd) | Actual Effort (pd) | Revised effort | pd
1 | Pre sales | Document of Understanding | N |  |  |  |  | First revision | 0
2 | Pre sales | Architecture Document | N |  |  |  |  | Second revision | 0
3 | Pre sales | Proposal | N
4 | Pre sales | Contract | N
5 | Requirement | Estimation | Y | 2 |  |  | 2
6 | Requirement | PMP | Y | 5 |  |  | 4
7 | Requirement | QAP | Y | 1 |  |  | 1
8 | Requirement | CMP | Y | 1 |  |  | 1
9 | Requirement | RMP | Y | 1 |  |  | 1
10 | Requirement | SRS | Y | 12 |  |  | 14
11 | Requirement | Requirement Traceability Matrix | Y | 3 |  |  | 2
12 | Analysis | Prototype/POC | N
13 | Analysis | Re-estimation-1 | N
14 | Analysis | Acceptance Test Plan | N
15 | Analysis | Acceptance Test Specification | N
16 | Design | HLD | Y | 20 |  |  | 24
17 | Design | System Test Plan | Y | 8 |  |  | 8
18 | Design | System Test Specification | Y | 15 |  |  | 18
19 | Design | LLD | N
20 | Design | Integration Test Plan | N
21 | Design | Integration Test Specification | N
22 | Design | Re-estimation-2 | N
23 | Development | Unit Test Plan | N
24 | Development | Unit Test Specification | Y | 20 |  |  | 18
25 | Development | Source Code | Y | 35 |  |  | 41
26 | Development | Unit Test Report | Y | 20 |  |  | 18
27 | Testing | Integration Test Report | N
28 | Testing | System Test Report | Y | 30 |  |  | 26
29 | Testing | User Manual | Y | 8
30 | Testing | Online Help | N
31 | Testing | Installation Guide | N
32 | Delivery | Release readiness check | Y | 1
33 | Delivery | Delivery note | Y | 1
33 | Delivery | Delivery note | Y | 1
34 |  | Project Management | Y | 27 |  |  | 20
35 | [6 empty] | 198

## Data sheet
Work Item | Del | Planned End Date | End Date | Estimated Effort pd | Cumulative Effort | Actual Effort pd | Cumulative AE | PC of completion | EV | Cumulative EV | Status on | 2023-01-23
Document of Understanding | N |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PV | 212
Architecture Document | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | AC | 198
Proposal | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | EV | 36
Contract | N |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | BAC | 210
Estimation | Y | 2022-10-03 | 2022-10-03 | 2 | 2 | 2 | 2 | 100 | 2 | 2 | Effort | 212
PMP | Y | 2022-10-10 | 2022-10-10 | 5 | 7 | 4 | 6 | 100 | 5 | 7
QAP | Y | 2022-10-04 | 2022-10-06 | 1 | 8 | 1 | 7 | 100 | 1 | 8
CMP | Y | 2022-10-06 | 2022-10-06 | 1 | 9 | 1 | 8 | 100 | 1 | 9
RMP | Y | 2022-10-07 | 2022-10-07 | 1 | 10 | 1 | 9 | 100 | 1 | 10
SRS | Y | 2022-10-12 | 2022-10-14 | 12 | 22 | 14 | 23 | 100 | 12 | 22
Requirement Traceability Matrix | Y | 2022-10-13 | 2022-10-14 | 3 | 25 | 2 | 25 | 100 | 3 | 25
Prototype/POC | N |  | 0 | 0 | 25 |  | 25 | 0 | 0 | 25
Re-estimation-1 | N |  | 0 | 0 | 25 |  | 25 | 0 | 0 | 25
Acceptance Test Plan | N |  | 0 | 0 | 25 | 0 | 25 | 60 | 0 | 25
Acceptance Test Specification | N |  | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 25
HLD | Y | 2022-10-25 | 2022-10-31 | 20 | 45 | 24 | 49 | 20 | 4 | 29
System Test Plan | Y | 2022-10-21 | 2022-10-26 | 8 | 53 | 8 | 57 | 90 | 7 | 36
System Test Specification | Y | 2022-11-24 | 2022-11-28 | 15 | 68 | 18 | 75 | 0 | 0 | 36
LLD | N |  | 0 | 0 | 68 |  | 75 | 0 | 0 | 36
Integration Test Plan | N |  | 0 | 0 | 68 |  | 75 | 0 | 0 | 36
Integration Test Specification | N |  | 0 | 0 | 68 |  | 75 | 0 | 0 | 36
Re-estimation-2 | N |  | 0 | 0 | 68 | 0 | 75 | 0 | 0 | 36
Unit Test Plan | N |  | 0 | 0 | 68 | 0 | 75 | 0 | 0 | 36
Unit Test Specification | Y | 2022-11-04 | 2022-11-11 | 20 | 88 | 18 | 93 | 0 | 0 | 36
Source Code | Y | 2022-12-14 | 2022-12-19 | 35 | 123 | 41 | 134 | 0 | 0 | 36
Unit Test Report | Y | 2023-01-02 | 2023-01-09 | 20 | 143 | 18 | 152 | 0 | 0 | 36
Integration Test Report | N |  | 0 | 0 | 143 |  | 152 | 0 | 0 | 36
System Test Report | Y | 2023-02-07 | 2023-02-16 | 30 | 173 | 26 | 178 | 0 | 0 | 36
User Manual | Y | 2023-02-20 | 0 | 8 | 181 | 0 | 178 | 0 | 0 | 36
Online Help | N |  | 0 | 0 | 181 |  | 178 |  |  | 36
Installation Guide | N |  | 0 | 0 | 181 | 0 | 178 | 0 | 0 | 36
Release readiness check | Y | 2023-02-27 | 0 | 1 | 182 | 0 | 178 | 0 | 0 | 36
Delivery note | Y | 2023-03-01 | 0 | 1 | 183 | 0 | 178 | 0 | 0 | 36
Release note | Y | 2023-03-01 | 0 | 27 | 210 | 20 | 198 | 0 | 0 | 36
Project management |  |  |  | 0 | 210 |  | 198 |  | 0 | 36

## EVM-Status
Project Name | Estimated
Integra CKYC Gateway | Schedule | 25 | Weeks
| Effort | 212 | Person days
Project start date | 2022-09-30 | Project end date |  | 2023-03-01
Status of the project on | 2023-01-23 | What does it mean?
Are we ahead or behind schedule? | -83.02% | The project is running behind schedule
How efficiently are we using our time? | 16.98% | Project is running at 17 percent efficiency
When is the project likely to complete? | 147.2222 | As on date, project will take 147 weeks to complete
Are we under or over budget? | -450% | The project is 450 percent over budget
How efficiently are we using our resources? | 18.18% | For each dollar spent, 18 cents are recovered
What is the remaining work likely to cost? | 957 | As on date, project will take 957 person days to complete
What is the entire project likely to cost? | 1155 | #N/A
How much will we be under or over budget? (Assuming the current trend to continue) | -355.7% | On completion, the project will be 356 percent over budget if current trend continues
How much will we be under or over budget? (Assuming the current trend will not continue) | -77.14% | On completion, the project will be 77 percent over budget if corrective actions are taken to remove the causes of variance as on date
How much of the total effort have been used till date? | 94.29% | As on date, 94 percent of effort have been used yielding 17 percentage of work product.

## Graph (hidden)
| Project performance status on | 2023-01-23
(Do not need to enter any data in this sheet.)

## HC-Status (hidden)
Health check summary report
Date of report | 2023-01-23
Project Name | Integra CKYC Gateway
Project ID | IMSICGD1
Project Manager | Harikrishna E
PQA | 0
Number of team members | 9
Process Compliance | 89.39%
Process non-compliance | 10.61%
SCM Compliance | 93.1%
SCM Non-compliance | 6.897%
This is a proprietary tool and should not be used without permission from Integra.

## SCM (hidden)
Configuration Library
Sl No | Name of the item/document | To be developed | Planned date | Date completed | Version No. | Approved | Development lib. | Test lib. | Baseline lib. | Baseline record | Project folder | Arch. Lib.
1 | Document of Understanding | N | 0
2 | Architecture Document | N | 0
3 | Proposal | N | 0 |  |  | 1 |  |  |  |  | 1
4 | Contract | N | 0 |  |  | 1 |  |  |  |  | 1
5 | Estimation | Y | 2022-10-03 |  |  | 1 |  |  |  |  | 1
6 | PMP | Y | 2022-10-10 |  |  | 1 | 1 | 1 | 1 | 1
7 | QAP | Y | 2022-10-04 |  |  | 1 | 1 | 1 | 1 | 1
8 | CMP | Y | 2022-10-06 |  |  | 1 | 1 | 1 | 1 | 1
9 | RMP | Y | 2022-10-07 |  |  | 1 | 1 | 1 | 1 | 1
10 | SRS | Y | 2022-10-12 |  |  | 1 | 1 | 1 | 1 | 1
11 | Requirement Traceability Matrix | Y | 2022-10-13 |  |  | 0 | 0
12 | Prototype/POC | N | 0
13 | Re-estimation-1 | N | 0
14 | Acceptance Test Plan | N | 0
15 | Acceptance Test Specification | N | 0
16 | HLD | Y | 2022-10-25
17 | System Test Plan | Y | 2022-10-21
18 | System Test Specification | Y | 2022-11-24
19 | LLD | N | 0
20 | Integration Test Plan | N | 0
21 | Integration Test Specification | N | 0
22 | Re-estimation-2 | N | 0
23 | Unit Test Plan | N | 0
24 | Unit Test Specification | Y | 2022-11-04
25 | Source Code | Y | 2022-12-14
26 | Unit Test Report | Y | 2023-01-02
27 | Integration Test Report | N | 0
28 | System Test Report | Y | 2023-02-07
29 | User Manual | Y | 2023-02-20
30 | Online Help | N | 0
31 | Installation Guide | N | 0
32 | Release readiness check | Y | 2023-02-27
33 | Delivery note | Y | 2023-03-01
34 | Release note | Y | 2023-03-01

## iPro-master (hidden)
iProdata-master
Project id | IMSICGD1 |  | Planned effort (pd) | 212 | Revised effort |  | 0 | Schedule in weeks | 25
Employee name | Start date | End date | Artefact name | Status | Size | Unit | Activity | Actual effort in hr | Iteration | Defects
Murthy A N | 2007-04-23 |  | DOU | Work in progress | 5 | Pages | Preparation of document | 12
Rishabh Jain |  |  | Project Management Plan | Work in progress | 6 | Pages | Review of document | 5 |  | 6
Shiranthi Vaz |  |  | Architecture Document
Phani Prasad N |  |  | Software Requirement Specification
Rajesh Kumar J |  |  | Software Requirement Specification
Asish Mohapatra |  |  | Software Requirement Specification
Kishor Kumar Sahu |  |  | Software Requirement Specification
Abhishek |  |  | System Test Plan
Murthy A N | 2007-04-23 |  | DOU
Rishabh Jain |  |  | Project Management Plan
Shiranthi Vaz
Phani Prasad N
Rajesh Kumar J
Asish Mohapatra
Kishor Kumar Sahu
Abhishek
Murthy A N |  |  | Architecture Document
Rishabh Jain
Shiranthi Vaz
Phani Prasad N
Rajesh Kumar J
Asish Mohapatra
Kishor Kumar Sahu
Abhishek
Murthy A N |  |  | Architecture Document
Rishabh Jain
Shiranthi Vaz
Phani Prasad N
Rajesh Kumar J
Asish Mohapatra
Kishor Kumar Sahu
Abhishek
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Work in progress
Murthy A N | 2007-04-23 |  | Software Requirement Specification | Completed
Murthy A N | 2007-04-23 |  | Software Requirement Specification | On hold
Murthy A N | 2007-04-23 | 2007-05-30 | Software Requirement Specification | Approved

## iProweind (hidden)
iProweind
Employee name | Start date | End date | Artefact name | Status | Size | Unit | Actual effort in hr | Iteration | Defects
Sanjay S R |  |  | DOU | Work in progress | 5 | Pages | 12
Ramanamurthy |  |  | Architecture Document | Work in progress | 6 | Pages | 5 |  | 6

## iProweart (hidden)
iProweart
Artefact name | Start date | End date | Status | Size | Unit | Actual effort in hr | Iteration | Defects
Document of Understanding |  |  | Work in progress | 5 | Pages | 12
Architecture Document |  |  | Work in progress | 6 | Pages | 5 |  | 6
Proposal
Contract
Estimation
PMP
QAP
CMP
RMP
SRS
Requirement Traceability Matrix
Prototype/POC
Re-estimation-1
Acceptance Test Plan
Acceptance Test Specification
HLD
System Test Plan
System Test Specification
LLD
Integration Test Plan
Integration Test Specification
Re-estimation-2
Unit Test Plan
Unit Test Specification
Source Code
Unit Test Report
Integration Test Report
System Test Report
User Manual
Online Help
Installation Guide
Release readiness check
Delivery note
Release note
Project Management
Note on A2: ====== ID#AAAAoxV_4FA Bhaskar (2023-01-20 14:37:16) Please do not remove any item from the list below.

## iPro-individual (hidden)
iProdata
Project id |  |  |  | Employee name | [5 empty] | Date
|  |  |  | Effort in hours |  |  | Schedule in days
Artefact name | Size | Unit | Activity | Planned | Revised | Actual | Planned | Revised | Actual | Iteration | Defect | Unit
Guidelines for filling the data sheet:
1. Artefact name: Please select the appropriate artefact from the list given. In case the particular item is not available please intimate to the PQA about it. 2. Size: The size should be entered as number only and then select the unit from the next colu
All data entry points are highlighted in tan

## Computation-EVM (hidden)
Schedule Variation (SV) | -176 | -0.83019 | The project is running behind schedule
Schedule Performance Index (SPI) | 0.16981 | 0.16981 | Project is running at 17 percent efficiency
Time Estimate At Completion (EACt) |  | 147.2222 | As on date, project will take 147 weeks to complete
Cost Variance (CV) | -162 | -4.5 | percent over budget
Cost Performance Index (CPI) | 0.18182 | 0.18182 | For each dollar spent, 18 cents are recovered
To Complete Performance Index (TCPI) |  | 14.5
Estimate At Completion (EAC) |  | 1155 | #N/A
Variance at Completion (VAC) | -747 | -3.5571 | On completion, the project will be 356 percent over budget if current trend continues
Estimate To Complete (ETC) |  | 957 | As on date, project will take 957 person days to complete
Estimate At Completion (EAC) |  | 372
Variance at Completion (VAC) |  | -0.77143 | On completion, the project will be 77 percent over budget if corrective actions are taken to remove the causes of variance as on date
[6 empty] | EAC | AC +BAC-EV | current variance will not occur in the future
The project is running on time | [6 empty] | AC +((BAC-EV)/CPI) | current variance = future variance
The project is running behind schedule
The project is running ahead of schedule |  |  |  | PV | 212
if corrective actions are taken to remove the causes of variance as on date |  | #N/A |  | AC | 198
percent under budget |  | 77 |  | EV | 36
percent over budget |  |  |  | BAC | 210
if current trend continues
As on date, project will take |  | 147
additional person days to complete than estimated |  |  |  | PC of effort used up | 0.94286 | 94 | As on date, 94 percent of effort have been used yielding 17 percentage of work product.
weeks to complete |  |  |  | Work realised | 0.17143 | 17
On completion, the project will be |  | 356
person days to complete |  | 957
For each dollar spent, |  | 18
cents are recovered
The project is |  | 4.5 | The project is 450 percent over budget
Project is running at
percent efficiency
As on date,
percent of effort have been used yielding
percentage of work product.

## Progress
| Project Kick off date | 2022-10-03 | No data entry required on this page!
| Project Closure date | 2022-03-01
Sl.No | Deliverables (as per contract) | Planned Start date | Planned Del date | Rev (1) Del date | Rev (2) Del date | Actual Del date
1 | Proposal
2 | Contract
3 | Estimation
4 | PMP
5 | QAP | 2022-10-03 | 2022-10-03
6 | CMP | 2022-10-04 | 2022-10-10
7 | RMP | 2022-10-04 | 2022-10-04
8 | SRS | 2022-10-05 | 2022-10-06
9 | Requirement Traceability Matrix | 2022-10-06 | 2022-10-07
10 | #N/A | 2022-10-06 | 2022-10-12
11 | Prototype/POC | 2022-10-13 | 2022-10-13
12 | Re-estimation-1
13 | Acceptance Test Plan
14 | Acceptance Test Specification
15 | System Test Plan
16 | System Test Specification | 2022-10-13 | 2022-10-25
17 | Integration Test Specification | 2022-10-13 | 2022-10-21
18 | HLD | 2022-10-24 | 2022-11-24
19 | LLD
20 | Re-estimation-2
21 | Unit Test Specification
22 | #N/A
23 | Unit Test Report | #N/A | #N/A | #N/A | #N/A
24 | Integration Test Report
25 | System Test Report | 2022-10-25 | 2022-11-04
26 | User Manual | 2022-11-02 | 2022-12-14
27 | Online Help | 2022-12-05 | 2023-01-02
28 | Release readiness check
29 | Delivery note | 2023-02-06 | 2023-02-20
30 | Release note
31 | Acceptance
32 | Warranty | 2023-02-21 | 2023-02-27

## Size (hidden)
| Estimated Size (LOC) | 8
| Revised Size (LOC) |  |  |  |  | Actual Size (LOC)
| Customer supplied code |  |  |  | New Modules
Sl.No | Module | Received (LOC) | Modified, Added (LOC) | Deleted (LOC) | Sl.No | Module | LOC
1 |  |  |  |  | 1
2 |  |  |  |  | 2
3 |  |  |  |  | 3
4 |  |  |  |  | 4
5 |  |  |  |  | 5
6 |  |  |  |  | 6
7 |  |  |  |  | 7
8 |  |  |  |  | 8
9 |  |  |  |  | 9
10 |  |  |  |  | 10
11 |  |  |  |  | 11
12 |  |  |  |  | 12
13 |  |  |  |  | 13
14 |  |  |  |  | 14
15 |  |  |  |  | 15
16 |  |  |  |  | 16
17 |  |  |  |  | 17
18 |  |  |  |  | 18
19 |  |  |  |  | 19
20 |  |  |  |  | 20
21 |  |  |  |  | 21
22 |  |  |  |  | 22
23 |  |  |  |  | 23
24 |  |  |  |  | 24
25 |  |  |  |  | 25
| Total (LOC) | 0 | 0 | 0 |  | Total (LOC) | 0
Note on F3: ====== ID#AAAAoxV_4E0 Bhaskar Jyoti Phukan (2023-01-20 14:37:16) Please fill this part only if code base is supplied by the customer.

## Metrics
Project Metric
| Computation | Requirement | Analysis | Design | Code | Code Review | Unit Test | Integration Test | System Test | Release Readiness | Acceptance | Overall
Schedule Variation |  | 0 | [9 empty] | 0
Effort variation |  | 0 | [9 empty] | 0
Defect Rate |  | 0 | [9 empty] | 0
Defect Removal Effectiveness |  | 0 | [9 empty] | 0
Defect Injection Rate |  | 0 | [9 empty] | 0
Customer Satisfaction Index |  | 0 | [9 empty] | 0
On time Delivery Index |  | 0 | [9 empty] | 0
Cost of Poor Quality |  | 0 | [9 empty] | 0
Size Variation |  | 0 | [9 empty] | 0
Requirement Stability Index |  | 0 | [9 empty] | 0
Productivity | 3 | 0 | [9 empty] | 0
Note on C3: ====== ID#AAAAoxV_4Ew Bhaskar Jyoti Phukan (2023-01-20 14:37:16) URS
Note on D3: ====== ID#AAAAoxV_4E4 Bhaskar Jyoti Phukan (2023-01-20 14:37:16) SRS

## Documents
Sl.No | Work Item | Version No | Size (P.Nos, Req.Tags) | Author | Date of Preparation | Preparation effort (person hrs) | Reviewer | Date of Review | Review effort (in min) | Review defects |  |  |  | Defect rate | Issues Fixed on | Rework effort (person hrs) | Verified
[10 empty] | Fatal | Major | Minor | Total
1 | SPMP
|  |  | 0 | [9 empty] | 0 | #DIV/0!
3 | SRS
#DIV/0!
4 | HLD
#DIV/0!
5 | LLD
6 | STP
7 | STS
8 | ITS
9 | UTS
10 | User Manual
11 | Online help
12 | Others if any

## Coding & UT
| CODING | [5 empty] | CODE REVIEW | [9 empty] | UTS- Preparation | [12 empty] | UNIT TESTING
Sl.No | Module Name | Version No | Size (LOC) | Author | Date of Preparation | Preparation effort (person hrs) | Reviewer | Date of Review | Review effort (in min) | Code Review defects |  |  |  | Issues Fixed on | Rework effort (person hrs) | Verified | Prepared by | Version No | Preparation effort (person hrs) | Reviewed by | Review date | Review effort (person hrs) | UTS - Review defects |  |  |  | Issues Fixed on | Rework effort (person hrs) | Verified | Done by | Done on | Testing effort (person hrs) | Unit Test defects |  |  |  | Issues Fixed on | Rework effort (person hrs) | Verified
[10 empty] | Fatal | Major | Minor | Total | [9 empty] | Fatal | Major | Minor | Total | [6 empty] | Fatal | Major | Minor | Total
Please do not modify any data in this row | [5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
1 | [12 empty] | 0 | [12 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
[13 empty] | 0 | [12 empty] | 0 | [9 empty] | 0
Please insert new row above this row. | [6 empty] | Please insert new row above this row. | [6 empty] | Please insert new row above this row. | [5 empty] | Please insert new row above this row. | [6 empty] | Please insert new row above this row. | [5 empty] | Please insert new row above this row.
Formulas:
Review effort (in min) = SUM([Review effort (in min), row below]:K105)

## IT (hidden)
INTEGRATION TESTING
Sl.No | Internal release version | Done by | Date | ITS Version ref | Testing effort (person hrs) | System Test defects |  |  |  | Issues Fixed on | Rework effort (person hrs) | Verified by
[6 empty] | Fatal | Major | Minor | Total
Please do not modify any cell value in this row |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0

## ST (hidden)
SYSTEM TESTING
Sl.No | Internal release version | Done by | Done on | STS version ref | Testing effort (person hrs) | System Test defects |  |  |  | Issues Fixed on | Rework effort (person hrs) | Verified
[6 empty] | Fatal | Major | Minor | Total
Please do not modify any cell value in this row. |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0

## Computation-HC
Please do not change any value in this sheet!
Process |  |  | Process compliance |  | 89.39% |  | Process non-compliance |  |  | 10.61%
List of deliverables of the project |  |  |  | 59 | 7
Sl No. | Item name | Available | Review | Review Record | Review Checklist | CVS | Total
1 | [6 empty] | 0
2 | [6 empty] | 0 |  | SCM compliance
3 | [6 empty] | 0 |  | Yes | 27
4 | [6 empty] | 0 |  | No's | 2
5 | Estimation | 1 | 1 | 1 | 0 | 1 | 4 |  | Compliance | 93.1%
6 | PMP | 1 | 1 | 1 | 0 | 1 | 4 |  | Non-comp | 6.897%
7 | QAP | 1 | 1 | 1 |  | 1 | 4
8 | CMP | 1 | 1 | 1 |  | 1 | 4
9 | RMP | 1 | 1 | 1 |  | 1 | 4
10 | SRS | 1 | 1 | 1 | 1 | 1 | 5
11 | Requirement Traceability Matrix | 0 | 0 | 0 | 0 | 0 | 0
12 | [6 empty] | 0 |  | Team size | 9
13 | [6 empty] | 0 |  | PM | 1 | Harikrishna E
14 | [6 empty] | 0 |  | Arch | 1 | Shailesh Ajmera
15 | [6 empty] | 0 |  | PL | 1
16 | HLD | 1 | 1 | 1 |  | 1 | 4 |  | TM | 6
17 | System Test Plan | 1 | 1 | 1 |  | 1 | 4
18 | System Test Specification | 1 | 1 | 1 |  | 1 | 4
19 | [6 empty] | 0
20 | [6 empty] | 0
21 | [6 empty] | 0
22 | [6 empty] | 0
23 | [6 empty] | 0
24 | Unit Test Specification | 1 | 1 | 1 |  | 1 | 4
25 | Source Code | 1 | 1 | 1 |  | 1 | 4
26 | Unit Test Report | 1 | 1 | 1 |  | 1 | 4
27 | [6 empty] | 0
28 | System Test Report | 1 | 1 |  |  | 1 | 3
29 | User Manual | 1 | 1 |  |  | 1 | 3
30 | [6 empty] | 0
31 | [6 empty] | 0
32 | Release readiness check | [5 empty] | 0
33 | Delivery note | 1 |  |  |  | 1 | 2
34 | Release note | 1 |  |  |  | 1 | 2
Configuration Library
Sl No | Name of the item/document | Approved | Development lib. | Test lib. | Baseline lib. | Baseline record | Project folder
1
2
3
4
5 | Estimation | 1 |  |  |  |  | 1
6 | PMP | 1 | 1 | 1 | 1 | 1 |  | PMP
7 | QAP | 1 | 1 | 1 | 1 | 1 |  | QAP
8 | CMP | 1 | 1 | 1 | 1 | 1 |  | CMP
9 | RMP | 1 | 1 | 1 | 1 | 1 |  | RMP
10 | SRS | 1 | 1 | 1 | 1 | 1 |  | SRS
11 | Requirement Traceability Matrix | 0 | 0
12
13
14
15
16 | HLD
17 | System Test Plan
18 | System Test Specification
19 | [7 empty] | LLD
20
21
22
23
24 | Unit Test Specification
25 | Source Code
26 | Unit Test Report
27
28 | System Test Report
29 | User Manual
30
31
32 | Release readiness check
33 | Delivery note
34 | Release note

## Risks
Identified risks in the project
1
2
3
4
5
6
7
8
9
10
Issues in the project
1
2
3
4
5
6
7
8
9
10

## Input (hidden)
Document of Understanding | Pages | Harikrishna E | Acquiring knowledge
Architecture Document | LOC | Shailesh Ajmera | Preparation of document
Proposal | Hours | Satyanarayana | Review of document
Contract | Days | 0 | Review of code
Estimation | Weeks | Pulok Barik | Rework
PMP | NOTC | Vaishnavi | Testing
QAP |  | Nafeesa NS | Attend Training
CMP |  | Suma Devi
RMP |  | Monika
SRS
Requirement Traceability Matrix
Prototype/POC
Acceptance Test Plan
Acceptance Test Specification
HLD
System Test Plan
System Test Specification
LLD
Integration Test Plan
Integration Test Specification
Unit Test Plan
Unit Test Specification
Source Code
Unit Test Report
Integration Test Report
System Test Report
User Manual
Online Help
Installation Guide
Release readiness check
Delivery note
Release note